## PCB_7Segment
Items No	Items to modify	Date Added	Estimated times	Actual Finished

	PCB layout V1 to V1.1
1	Increase hole side for connector E_PORTA, PORT2 to 40 mil			21/6/07
	( Change from SIP10 to IDC 10 footprint)	26/01/07		21/6/07
2	Increase ground plane clearance to 20 mil	26/01/07		21/6/07
3	Change RX to move outside	29/1/07		21/6/07
4	Move R1 R2 to beside Tr	29/1/07		Put to near signal line
5	Move Distacnce between SW, Speaker and 7 Segments to LEGO block units	29/1/07		21/6/07
6	Jumper hole too small	29/1/07		Remove jumper
7	Remove J1 from select SW connect between int pin and PB3 pin	21/6/07		Don't see necessary

## PCB_MEGA32
Items No	Items to modify	Date Added	Estimated times	Actual Finished

	PCB layout V1 to V1.1
1	Increase hole side for connector PORT1-3, I2C Port to 40 mil	26/01/07		21/2/07
	( Change from SIP10 to IDC 10 footprint)	26/01/07		21/2/07
2	Serial port hole does not fit	26/01/07		21/2/07
3	Jumper hole too small	29/01/07		21/2/07
4	Ground plane clearance to 20 mils	26/01/07		21/2/07
5	Battery holder too big	26/01/07		21/2/07
6	Power port hole too small	26/01/07		21/2/07
7	Move C8 from SOCKET programming	26/01/07		21/2/07
8	Check connectors	26/01/07		21/2/07
9	MAX232 line switch			21/2/07
	TX-OUT (13) Max 232
	RX-IN - (12) MAX 232	06/02/07

## Package
Items No	Items to modify	Date Added	Estimated times	Actual Finished

## Software
Items No	Items to modify	Date Added	Estimated times	Actual Finished	Notes

## Application
Items No	Items to modify	Date Added	Estimated times	Actual Finished