## SW Test Case
Requirement (R) /Design (D) Number	Number	Test Case	Date	Expected result	Actual result	Passed	Bug tracking No.
Display Mode
H-1-1		Display three color all dots		Show RED, GREEN, BLUE all dots
H-1-1, S-1-3		Change to each display mode and the dots is not blink		All display mode LED show without blink
		Insert graphic characters in text mode

Keyboard
H-3,S-3,S-6-1		Enter Thai /English character all characters		Switch and enter Thai/English characters
		Change color for each column		Press F3 to change color for each column

## HW Test Case
Requirement (R) /Design (D) Number	Number	Test Case	Date	Expected result	Actual result	Passed	Bug tracking No.
Power consumption
		Power volage / Current consumption		Should within 4.8 to 5.0 less than 1 Amp
		Voltage on each components		Should within 4.8 to 5.0
		Current through LED

## Bug Tracking
No	Date	Bug	Test Case #	Resolved Date	Troubleshooting	Duration to Fix
1	10/7/48	Push Reset button and sometime characters is missing			Voltage drop
2	12/7/48	Voltage drop some characters is missing			Voltage unstable Seperate Vled and Vdigital
3	26/7/48	When select next message mode. Message will change after other message finished show	17		next_slot change need to set buffer_change =1
4	26/7/48	Cannot show next message	17		next_slot change need to set buffer_change =1
5	28/4/49	Green line at column 32			Check PCB maybe short between SIN of TLC5921 and SOUT	5 Days

## Document tracking
Date	Revision	Modified by	Change tracking
25/07/2548	1	Wichai	Initial test case
/04/2550	1.1	Wichai	Update bug tracking

Note
	Test here is only functional testing
	At Final stage, coverage testing need to perform

Note on how to fill form